## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | PKM; 02/22/19 | Pass | PKM; 03/03/19 | Pass | PKM; 04/15/19
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name. | Pass | PKM; 02/22/19 | Pass | PKM; 03/03/19 | Pass | PKM; 04/15/19
| Given that no one else is using my name when I enter my name in the sign-in form and click the Sign-in button then I expect system to reserve my name and navigate back to the Home page. | Pass | PKM; 02/22/19 | Pass | PKM; 03/03/19 | Pass | PKM; 04/15/19
| Given that no one else is using my name when I enter a name with a double quote (`"`) then I expect the system to reject this name and return the sign-in form. (Note: double quote is not a valid character in a Player's name.) | Pass | PKM; 02/22/19 | Pass | PKM; 03/03/19 | Pass | PKM; 04/15/19
| Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the sign-in form. I can then choose a different user name. | Pass | PKM; 02/22/19 | Pass | PKM; 03/03/19 | Pass | PKM; 04/15/19
| Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) Thus the sign-in and sign-out links need to alternate and never been seen together or not at all. | Pass | PKM; 02/22/19 | Pass | PKM; 03/03/19 | Pass | PKM; 04/15/19
| Given that I am signed-in when I click on the sign-out link then I expect the system to sign me out, release my name for use by other users, and then return me to the Home page. | Pass | PKM; 02/22/19; Fixed issue that did not allow players to log out from the game screen | Pass | PKM; 03/03/19 | Pass | PKM; 04/15/19
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | PKM; 02/22/19; Fixed issue that listed all players as in game instead of waiting | Pass | PKM; 03/03/19 | Pass | PKM; 04/15/19
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | PKM; 02/22/19 | Pass | PKM; 03/03/19 | Pass | PKM; 04/15/19
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. |  |  | Pass | PKM; 03/03/19; Ajax notes that turn cycle does not exist. Fine for this sprint, implement later. | Pass | PKM; 04/15/19
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. |  |  | Pass | PKM; 03/03/19 | Pass | PKM; 04/15/19
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. |  |  | Pass | PKM; 03/03/19 | Pass | PKM; 04/15/19
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. |  |  | Pass | PKM; 03/03/19 | Pass | PKM; 04/15/19
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. |  |  | Pass | PKM; 03/03/19 | Pass | PKM; 04/15/19
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. |  |  | Pass | PKM; 03/03/19 | Pass | PKM; 04/15/19
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. |  |  | Pass | PKM; 03/03/19; Piece is droppable on any valid space disregarding movement rules. Turn system unimplemented, so Ajax call says there is an error. | Pass | PKM; 04/15/19
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. |  |  | Pass | PKM; 03/03/19 | Pass | PKM; 04/15/19
As a player I want to wait while my opponent makes their move so that we can alternate turns. | Given I have ended my turn when my opponent begins their turn then I expect to wait until my opponent has finished to begin my turn. |  |  | Pass | PKM; 03/31/19 | Pass | PKM; 04/15/19
| Given my oppoent has finished their turn when my turn begins then I expect to see an updated game board. |  |  | Pass | PKM; 03/31/19 | Pass | PKM; 04/15/19
| Given I am waiting for my opponent to finish their turn when I resign then I expect the game to end. |  |  | Pass | PKM; 03/31/19; When the opponent resigns, you are presented the win message. To exit you must either resign or log out. | Pass | PKM; 04/15/19
As a player I want to be able to resign from a game so that I can end the game prematurely. | Given that it is my turn when I have not made any moves then the Resign button should be enabled. |  |  | Pass | PKM; 03/31/19 | Pass | PKM; 04/15/19
| Given the resign button is enabled when I click it then I expect the game to end and my opponent to be awarded the victory. |  |  | Pass | PKM; 03/31/19 | Pass | PKM; 04/15/19
| Given it is my turn when I make a valid move then the Resign button should be disabled. |  |  | Pass | PKM; 03/31/19 | Pass | PKM; 04/15/19
As a player I want to make a single move so that the game can progress. | Given it is my turn when I drop a piece into an open space then all other pieces should be disabled except for the start piece |  |  | Pass | PKM; 03/31/19 | Pass | PKM; 04/15/19
| Given I have dropped a piece into an invalid space when the server recognizes the move as invalid then I expect to see an error message telling me the move is invalid. |  |  | Pass | PKM; 03/31/19 | Pass | PKM; 04/15/19
| Given I have made a move with the start piece when I drop the start piece into another pen space then I expect the turn to go through the same validation a single move would require. |  |  | Pass | PKM; 03/31/19 | Pass | PKM; 04/15/19
| Given I have made an invalid move when the error message appears then my pieces should be re-enabled, and my piece should be moved back into the start location. |  |  | Pass | PKM; 03/31/19 | Pass | PKM; 04/15/19
| Given I have made a valid move when I click the Backup button then I expect my most recent move to be undone. |  |  | Pass | PKM; 03/31/19 | Pass | PKM; 04/15/19
| Given I have not made any moves when I click the Backup button then all buttons should be disabled and my pieces should be enabled. |  |  | Pass | PKM; 03/31/19 | Pass | PKM; 04/15/19
| Given I have made a valid move when I click the Submit button then I expect the page to reload and display my move. |  |  | Pass | PKM; 03/31/19 | Pass | PKM; 04/15/19
| Given I have made an invalid move when I click the Submit button then I expect to be shown an error message referring to the invalid turn. |  |  | Pass | PKM; 03/31/19; Players are unable to make invalid turns due to move validation. Will update if a flaw is found. | Pass | PKM; 04/15/19
| Given I have submitted a valid turn when the server confirms that the turn is valid then I expect the page to display the move for both myself and my opponent. |  |  | Pass | PKM; 03/31/19 | Pass | PKM; 04/15/19
As a player I want to see if my move was valid so that I can progress through the game | Given it is my turn when I move a piece then I expect the application to confirm that the move is valid or not. |  |  | Pass | PKM; 03/31/19 | Pass | PKM; 04/15/19
| Given my move is not valid when I confirm it, then I expect to be told the move is invalid. |  |  | Pass | PKM; 03/31/19 | Pass | PKM; 04/15/19
| Given my moved is valid when I confirm it then I expect to be able to make the move. |  |  | Pass | PKM; 03/31/19 | Pass | PKM; 04/15/19
As a player I want to be able to change my normal pieces to kings so that they can move both forward and back. | Given a piece makes it to the side of the board opposite the side it started when I move the piece into that section of the board then I expect the application to 'king' that piece. |  |  | Pass | PKM; 03/31/19 | Pass | PKM; 04/15/19
| Given one of my pieces is kinged when I move that piece then I expect the piece to be able to move both forward and back. |  |  | Pass | PKM; 03/31/19 | Pass | PKM; 04/15/19
As a player I want to jump a piece so that I can capture an opponent's checkers and win a game. | Given I have an opposing piece diagonal to mine when I jump it then the opposing piece is removed from the board. |  |  | Pass | PKM; 03/31/19 | Pass | PKM; 04/15/19
| Given I have chosen to make multiple jumps when I submit the move then I expect it to complete all the jumps. |  |  | Pass | PKM; 03/31/19 | Pass | PKM; 04/15/19
As a player I want to make a double jump or more so that I can capture multiple opposing pieces in one turn. | Given there are multiple opposing pieces along a given line when I choose to jump an opponent's piece then I jump all pieces availible in the line. |  |  | Pass | PKM; 03/31/19 | Pass | PKM; 04/15/19
| Given I make a jump and a subsequent jump is availible when I try to submit my turn then I should be told that it is a valid move. |  |  | Pass | PKM; 03/31/19 | Pass | PKM; 04/15/19
As a player, I want to be able to review the replays of games I have players so that I can watch the game again. | Given that I have logged into an account, when I look at the display then I expect to see a place where a replay of the most recent game is stored. |  |  |  |  | Pass | PKM; 04/15/19;
| Given I have played a game of checkers, when I navigate back to the home tab then I expect to see a place where the most recent game I have played is stored. |  |  |  |  | Pass | PKM; 04/15/19; Technically passes, however the game is not displaying for the challenged party. Error fixed, log updated.
| Given I play a game when a recording is already stored, when I view the record of the last game played then I expect it to have overwritten the previous game. |  |  |  |  | Pass | PKM; 04/15/19; The previous recording is overwritten.
As a player, I want to be able to challenge an artificial intelligence so that I can play a game without having to challenge another living person. | Given I select a game with an AI player when the game begins then I expect to be placed into a game with an AI |  |  |  |  | Pass | PKM; 04/15/19
| Given I am placed into a game with an artificial player when it is the AI's turn, then I expect them to make a legal move. |  |  |  |  | Pass | PKM; 04/15/19; I tested it, and looked at the code. It looks like everything works, and the AI has yet to make an illegal move.